## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story /Feature Description | MoSCoW | Dependency | Assignee | Status
S1 | S1 | US-001 | Develop an intelligent model to automatically categorize support tickets and predict likely resolutions, minimizing the need for manual triage. | Must |  | T. Udaya Sindhu | Completed
S2 | S2 | US-002 | Create an intuitive interface that allows customers to submit support tickets and monitor their status with clear, real-time updates. | Should | 1 | T. Udaya Sindhu | Completed
S3 | S3 | US-003 | Integrate the ML engine with the user interface to provide users and agents with real-time auto-suggestions for faster issue resolution. | Must | 2 | T. Udaya Sindhu | Completed
S4 | S4 | US-004 | Leverage RAG to analyze ticket text for sentiment and context, facilitating effective prioritization and improving response accuracy. | Must | 3 | T. Udaya Sindhu | Completed
S5 | S5 | US-005 | Build a dashboard featuring metrics, visual charts, and alerts to enable managers to effectively monitor team performance and operational efficiency. | Should | 4 | T. Udaya Sindhu | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate (hours)
US-01 | T-01 | Integrate ticket data through Google Sheets for seamless data access and management. | Aug 14th | Aug 19th | T. Udaya Sindhu | Integration | Done | 9
US-02 | T-02 | Gather and clean historical ticket data to prepare it for analysis. | Aug 20th | Aug 22th | T. Udaya Sindhu | Data Preprocessing | Done | 8
US-03 | T-03 | Develop a RAG model to generate accurate responses for support tickets. | Aug 23th | Aug 27th | T. Udaya Sindhu | Model Development | Done | 6
US-04 | T-04 | Implement LLMs to automatically categorize support tickets for better organization. | Aug 28th | Sep 2th | T. Udaya Sindhu | Model Integration | Done | 7
US-05 | T-05 | Conduct testing of the model on a pilot dataset to validate performance. | Sep 3th | Sep 7th | T. Udaya Sindhu | Testing | Done | 9
US-06 | T-06 | Clean and preprocess ticket data to ensure high-quality inputs for the model. | Sep 8th | Sep 13th | T. Udaya Sindhu | Data Cleaning | Done | 8
US-07 | T-07 | Develop an AI-powered chatbot to assist users by resolving their queries efficiently. | Sep 14th | Sep 18th | T. Udaya Sindhu | Development | Done | 6
US-08 | T-08 | Integrate RAG model and Tabuli search tools to enhance system capabilities. | Sep 19th | Sep 23th | T. Udaya Sindhu | Integration | Done | 9
US-09 | T-09 | Implement real-time article recommendations to support users with relevant information. | Sep 24th | Sep 27th | T. Udaya Sindhu | Feature Enhancement | Done | 8
US-10 | T-10 | Create an analytical dashboard to visualize key metrics and insights. | Sep 28th | Sep 30th | T. Udaya Sindhu | Dashboard | Done | 7
US-11 | T-11 | Develop dashboards and Slack alerts to monitor system performance and notify stakeholders. | Oct 1th | Oct 3th | T. Udaya Sindhu | Monitoring | Done | 5

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 13th August | Received initial guidelines and clarification required to commence the project. | Initiated project setup and began preliminary tasks.
Sprint 2 | 21nd August | Needed to establish the project workflow and define objectives for Sprint 1. | Designed the project workflow and created the required dataset for Sprint 1.
Sprint 3 | 5th September | Required further analysis of the model and clarification regarding Sprint 2 planning. | Integrated the model with Google Sheets and began developing the user interface.
Sprint 4 | 13th September | Encountered issues related to model accuracy and exceeding the allocated quota limits. | Optimized the model configuration and updated the chat and embedding modules.
Sprint 5 | 24nd September | Needed detailed discussion on Sprint 3 tasks and implementation of the alert system. | Conducted coverage analysis and refined the alert system functionality.
Sprint 6 | 1sh October | Required final validation of the user interface and implementation of necessary corrections. | Completed UI finalization and applied all identified improvements.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | Aug 13th | Aug 30th | T.Udaya Sindhu | Initiated integration of project components with Google Sheets. | Discontinued manual data collection processes. | Continued enhancement of the Retrieval-Augmented Generation (RAG) model. | Implemented preprocessing procedures to streamline data handling.
2 | Sprint 2 | Sept 2th | Sept 12th | T.Udaya Sindhu | Began categorizing and organizing support tickets for analysis. | Halted model testing using the preliminary pilot dataset. | Continued refining data preprocessing workflows. | Validated the pilot dataset and ensured accuracy of data mapping.
3 | Sprint 3 | Sept 13th | Sept 23th | T.Udaya Sindhu | Commenced development of the AI-driven agent for automation. | Suspended real-time article recommendation module for optimization. | Continued enhancement of the analytical dashboard features. | Successfully integrated the RAG and Tabuli search functionalities.
4 | Sprint 4 | Sept 24th | Oct 4th | T.Udaya Sindhu | Initiated configuration and monitoring of the alert system setup. | Discontinued redundant alert checks to optimize system performance. | Continued refinement of alert monitoring and notification workflows. | Deployed and tested the alert system with stable monitoring features.